## CP1_CP2
CP1 |  |  |  | CP4
TestNum | Item | State | 说明 | TestNum | Item | State
1 | OS_Test | PASS |  | 1 | OS_Test | PASS
2 | Enter_Eot_Test | PASS | 降频测试 | 2 | Enter_Eot_Test | PASS
20 | Read_Array_FF_Lo_Test | PASS |  | 3 | Read_Array_00_Lo_Test | PASS
60 | Read_Array_FF_Hi_Test | PASS |  | 4 | Read_Array_00_Hi_Test | PASS
5 | Off_Margin_Read_Array_FF_Std_Test | PASS |  | 5 | Margin_Read_Array_00_Std_Test | PASS
6 | PGM_DIAG_Weakness_Test | PASS
7 | Read_DIAG_Weakness_Lo_Test | PASS
8 | Read_DIAG_Weakness_Hi_Test | PASS
9 | PGM_DIAG_Test | PASS
10 | Read_DIAG_Lo_Test | PASS
11 | Read_DIAG_Hi_Test | PASS
12 | Off_Margin_Read_DIAG_Std_Test | PASS
13 | PGM_CKBD_Test | PASS
14 | Read_CKBD_Lo_Test | PASS
15 | Read_CKBD_Hi_Test | PASS
16 | Off_Margin_Read_CKBD_Std_Test | PASS
17 | PGM_CKBDN_Test | PASS
18 | Read_Array_00_Lo_Test | PASS
19 | Read_Array_00_Hi_Test | PASS
20 | Margin_Read_Array_00_Std_Test | PASS
备注：State状态栏"P"表示已经调试完成项目，剩余项目未完成。

## CP3_CP4
CP3 |  |  |  | CP4
TestNum | Item | State | 说明 | TestNum | Item | State
1 | OS_Test | P |  | 1 | OS_Test
2 | Enter_Eot_Test | P |  | 2 | Enter_Eot_Test
20 | Off_Margin_Read_Array_FF_Std_Test | P |  | 3 | Read_Array_FF_Lo_Test
60 | VDDLDO_Trim_Test | P |  | 10 | Read_Array_FF_Hi_Test
5 | VDDLDO_1D8_Trim_Test | P |  | 20 | Off_Margin_Read_Array_FF_Std_Test
6 | Vref_Trim_Test | P |  | 40 | ATPG_Test
7 | OSC2M_Trim_Test | P |  | 50 | RAM_BIST_Test
8 | ADC_Test | F | 电压值偏离spec。 | 90 | Leakage_Test
9 | TS_Test1 | P |  | 100 | VIHL_Test
10 | TS_Test2 | P |  | 110 | VOL_Test
11 | IP_Trim_Write_Test | F | run pattern fail,待查找原因 | 120 | VOH_Test
12 | load_ucode | F | run pattern fail,待查找原因。 | 150 | LD_Test0
13 | idd_ramist | F | 电流偏大 | 150 | LCD_Test
14 | Istand_Test | F | 电流偏大 | 60 | VDDLDO_Trim_Test
15 | Write_CP3_GDFLG_Test |  |  | 70 | Vref_Trim_Test
|  |  |  | 85 | OSC2M_Trim_Test
|  |  |  | 150 | ADC_Test
|  |  |  | 150 | TS_Test1
|  |  |  | 155 | TS_Test2
|  |  |  | 86 | Write_Key_Test
|  |  |  | 85 | IP_Trim_Write_Test
|  |  |  | 160 | SN_NUM
|  |  |  | 140 | Istand_Test
|  |  |  | 222 | Write_CP4_GDFLG_Test
|  |  |  | 300 | Read_Data_Test
备注：State状态栏"P"表示已经调试完成项目，剩余项目未完成。